## Stakeholder analysis
No. | Stakeholder | Role / group | Influence (1–5) | Interest (1–5) | Attitude | Strategy (automatic) | Action | Owner | Next date
1 | Managing director | Sponsor | 5 | 4 | supportive |  | Monthly steering committee, milestone sign-off | Project lead
2 | Works council | Co-determination | 4 | 5 | critical |  | Involve early, conclude works agreement before go-live | Head of HR
3 | Head of IT | Technical owner | 4 | 5 | supportive |  | Core team member, joint architecture decisions | Project lead
4 | Head of production | Users | 4 | 3 | critical |  | Clarify downtime concerns, pilot on one line | Project lead
5 | Warehouse team | Users | 2 | 4 | critical |  | Name key users, training before go-live | Warehouse sub-project lead
6 | Data protection officer | Advisory | 3 | 3 | neutral |  | Review record of processing and DPA | Head of IT
7 | Sales | Users | 3 | 2 | neutral |  | Inform about changes to order processes | Head of sales
8 | Tax adviser | External | 2 | 2 | neutral |  | Agree the accounting interface | Accounting
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## How to use
How to use this template
1. List everyone involved: people, groups, committees, external partners.
2. Rate influence and interest from 1 (very low) to 5 (very high) and pick the attitude from the list.
3. The strategy is calculated: influence ≥ 3 and interest ≥ 3 = manage closely; influence ≥ 3, interest < 3 = keep satisfied; influence < 3, interest ≥ 3 = keep informed; otherwise monitor.
4. Set a concrete action, an owner and the next date for each stakeholder.
5. Address critical stakeholders with high influence (marked red) first.
The sample rows show an ERP rollout. Overwrite or delete them.
Interactive matrix with export: https://pathhub.ai/en/tools/stakeholder-analysis.html